## Sheet1
Date | Item | Status
2018-10-17 | Calculate Target Gross Margin % | done
2018-10-17 | When printing, make Accessorials optional | done
2018-10-22 | Add Piece/Shipment choices to all accessorials in interface | done | only Dangerous Goods
2018-10-22 | SAP File format changing to accommodate piece/shipment |  | Change report also to add these columns
2018-10-17 | Need ability to add attachments (Can be Phase 2)
2018-10-22 | Reformat Report for Contracts - one line per Contract with Notes concatenated | done
2018-10-23 | Hide Get Revenue button on New entries if not pricing group
2018-10-23 | Rework Fuel Discount interface | done
2018-10-23 | Add Beyond yes or no to interface | done
2018-10-23 | Add report: renewal sheet |  | pricing only comments - get list of columns
2018-10-24 | Express, Brokerage and Other - all go into other revenue | done
2018-10-24 | Unhide 'Other' if it has revenue | done
2018-10-25 | Do we need an export to Excel function for one contract |  | Without all the extra columns
2018-10-25 | Will we need a detail backup report for Target Gr Margin %
2018-10-25 | Will we need a Maintenance (or upload) for the Gr Margin % matrix
2018-10-25 | Other boxes - if showing from getRev, gets messed up |  | I think it's ok
2018-10-25 | Margin % and Target Gross Margin % - remove from middle cols?
2018-10-25 | Fill in New Margin %?